{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["Sheet1","Sheet2"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":23,"n_cols":11,"rows_kept":23,"cut":false,"hidden":false,"merged":[[9,1,9,9],[2,1,2,9],[0,3,0,6]]}
["Sv","Product Backlog",null," Hanno's proposal for Items to consider"]
[null,"Task","Redmine Issue(s) related to this","Item Lead","Team members involved","Non-team PI","User Story","Acceptance Criteria","Specifications","Documentation"]
[null,"ITEMS USED AS INPUT TO SPRINT 1.11 (Jan 14 - Feb 4)"]
[1,"Ingest Raw BF data - \nDiscuss the implementation and implement required functionality","#4020, 4047- 4051","Adriaan","Jan David, Ruud, Nico","Fallows","As a support scientist/observer I need to:\nIngest BF data to the LTA \nNeed to tie-up the loose ends that came up with latest changes of the BF observation definition.","Ingest of Raw Beam Formed data"]
[6,"CEP2 Data Managing System: Investigate what is needed and what is already available",null,"Adriaan Alwin",null,"Roberto","As a support scientist and observer  I need the tools to \na) display all used disk space in CEP 2 disks\nb)  manage this disk space (in SCHEDULER at the moment)"]
[9,"Investigate improvements to framework to enable Batch Scheduling and feedback of pipelines",null,"Alwin","Wouter, Marcel",{"$nulls":4},"Replaces previous items on DPU and Batch scheduling"]
[13,"Implement \"Black box\" Pulsar pipeline",null,"Alwin","Alwin, Nico, Adriaan",null,"Meeting held Sprint 1.11; define tasks for later implementation"]
[14,"MSSS raw data \"auto\" archive: requirement workshop",null,"Hanno",null,null,"For HBA MSSS observations we also need to archive the raw data. \nInvestigate whether this can be done in a pipeline fashion."]
[]
[null,"ITEMS THAT SHOULD BE ESTIMATED AND PRIORITISED FOR FOLLOWING SPRINTS"]
[" ","Improve Storage Calculations (web applications)",null,"Holties","Boelen\n(EXTERNAL will work flexibly)","Frieswijk, Pizzo","As a user/support scientist I need to:\nbe able to calculate the expected data size of observations as they are:\na) proposed (NorthStar)\nb) set-up (MoM-Scheduler)","a) Extension of existing calculators in Web/MoM with more user defined entries.\nb) Web page \"Online Calculator\" redesigned"]
[" ","Discuss LTA ingest of other interferometry final data (e.g., catalogues, plots, except for images)",null,"Adriaan","Form a group to define what are the final data!","Polatidis, Jozsa, Heald,Pizzo","As an support scientist\n    I want to be able to ingest final products of interferometry data to the LTA (images catalogues, plots) , through MoM","a) Succesfully ingest final products of interferometry data to the LTA.\nb) Query (simple) of these datasets\nc) Download (e.g.FTP) the data from a user.",null,null,"Reconsidee short term and long term needs for dataproducts that the LTA should support"]
[null,"USER INGEST mechanism",null,null,"Adriaan",null,"As a user I need to be able to ingest my final products to the LTA","a) Succesfully Import processed Interferometry data\nb)Succesfully ingest final images\nc) Succesfully import processed PULSAR data"]
[null,"Installation of LOFAR processing software outside CEP",null,null,"Adriaan, Wouter"]
[null,"Improve robustness LTA ingest pipeline",null,null,"Adriaan"]
[" ","LTA Ingest of processed beamformed data products",null,"Adriaan",null,"Fallows, Hessels","a) Pulsar pipeline products\nb) Dynamic Spectra"]
[" ","Discuss Revision MoM-Northstar interface.\nPostponed for 1.12",null,"Hanno","Hanno, Nico","Frieswijk, Polatidis","As a support scientist\n    I want to import all the characteristics of the observations as they have been proposed in Northstar to MoM.","1) The fields in NorthStar should have a correspondence in MoM.\n2) Successful transfer of all possible observing modes to a MoM Template (using example proposals)","Will define the specification during Sprint 1.7. It could be delayed given the evolution of XML script"]
[" ","New Export-GUI for the LTA (EPIC)",null,null,"Nico, Adriaan",null,"As an support scientist\n    I want to be able to use a GUI to ingest to the LTA, through MoM"]
[null,"Transfer maintenance of LTA UI (Astrowise) and related interfaces to ASTRON"]
[null,"LTA Preview Images and Cutout Server","3509","Adriaan",null,null,"Design the Cutout server implementation"]
[null,"Manually Pipeline process and ingest BF+correlated data products"]
[null,"Automatically Pipeline process and ingest BF+correlated data products"]
[null,"LTA Ingest of TBB data",null,"Adriaan","Alexander, Jan David, Nico","van den Aker, Schellart","We need to ingest TBB dumps to the LTA","a)Archive data \nb)Connect it to \"paternal\" observation if piggybacking c)Retrieval of data by User"]

{"sheet":"Sheet2","index":1,"n_rows":4,"n_cols":7,"rows_kept":4,"cut":false,"hidden":false,"merged":[]}
[null,"FINISHED RECENTLY"]
[]
[null,"a) Enable NDPPP demixing in manual pipeline for MSSS \n\nb) Enable NDPPP demixing in manual pipeline for non-MSSS observation #3406","Marcel","Marcel, Ger (b. #3406 recipe changed by Horneffer, verified ?)","Pizzo,(finishing?)","As a support Scientist\nI need NDPPP demixing to the manual pipeline\nto process old (existing) data and other data that will be observed in the next few weeks.","Successfully run in the “manual” pipeline"]
[null,"LTA ingest of raw interferometer and beam formed data","Adriaan","IN PROGRESS","Frieswijk, Fallows","As an support scientist\n    I want to be able to ingest interferometry raw data and raw beamformed data to the LTA, through MoM","a) Successful ingest to the LTA of raw interferometry and Beam formed data, through MoM  \nb) Query (simple) of these datasets\nc) Download (e.g. FTP) the data from a user."]